## Sheet1
Task | Expected Time to Complete | Actual Time to Complete
Setup Scene | 10 minutes | 10
Add Player Model | 5 minutes | 5
Setup Player input | 10 minutes | 15
Add Pickups (Soldiers) | 10 minutes | 5
Add Home base | 5 Minutes | 5
Add Obstacles | 5 Minutes | 5
Add Collisions | 10 Minutes | 15
Implement Soldier Counters | 15 Minutes | 20
Implement drop off at base | 15 Minutes | 10
Add Lose and Win Screens | 10 Minutes
Add Reset button | 5 Minutes